## Sheet1
Spr No | Assignee | Project | Headline | Description | Status | Milestone | Reported Version | Resolved Version | initial_steps | is_reproducable | why1 | answer1 | why2 | answer2 | why3 | answer3 | why4 | answer4 | why5 | answer5 | new_status_time | assigned_status_time | resolved_status_time | validated_status_time
SPR100 | Alice | CT | CT scan image viewer not loading properly | The image viewer freezes when loading DICOM series in sequence. | Assigned | Stability Patch | 2.3.4 | - | Issue reproduced in test environment, logs collected. | Yes | Why does the viewer freeze? | Thread pool exhaustion due to high-res image processing. | Why is the pool exhausted? | Image loading is synchronous and blocks rendering thread. | Why is it synchronous? | Legacy code in Java Swing event dispatch thread. | Why is legacy code still used? | Refactoring plan delayed due to Q1 deadline. | Why was the deadline prioritized? | Customer demo required stable old features.
SPR101 | Bob | CT | Angular module crashes on patient report fetch | Clicking 'Fetch Reports' crashes the embedded Angular module intermittently. | In Progress | Q3 Roadmap | 1.1.2 | - | Issue reproduced in test environment, logs collected. | Yes | Why does the module crash? | Uncaught promise rejection on HTTP error. | Why is it uncaught? | Missing error handler in Angular service. | Why is handler missing? | Developer assumed HTTP interceptor would catch all errors. | Why is assumption wrong? | Interceptor only logs, doesn’t handle rejections. | Why wasn’t it caught in testing? | No test case for 404 response path.
SPR102 | Clara | CT | Delayed UI response during scan configuration | UI takes over 10 seconds to respond when configuring scan presets. | New | Q2 Fixes | 3.0.1 | - | Issue reproduced in test environment, logs collected. | Yes | Why is UI delayed? | Angular change detection takes too long. | Why is change detection slow? | Too many bound variables in scan config form. | Why so many variables? | All form fields are bound two-way unnecessarily. | Why was two-way binding used? | Copied from another module without optimization. | Why wasn't it reviewed? | Time constraints during integration sprint.
SPR103 | David | CT | NullPointerException in scan scheduler backend | Backend throws NullPointerException when scheduling overlapping scans. | Resolved | Hotfix Batch | 1.0.0 | 4.1.0 | Issue reproduced in test environment, logs collected. | Yes | Why NPE in backend? | Null patient object passed to scheduler. | Why is patient null? | Scheduler triggered before patient assignment completes. | Why trigger before assignment? | Scan request UI sends async event prematurely. | Why is event premature? | UI does not await SpringBoot response completion. | Why doesn’t UI await response? | Missing promise chaining in embedded Angular.
SPR104 | Eva | CT | Database connection leak in system monitor | System monitor fails to release DB connections after polling logs. | Assigned | Stability Patch | 4.1.0 | - | Issue reproduced in test environment, logs collected. | Yes | Why connection leak? | Connections not closed in polling loop. | Why not closed? | Logger service forgets to release resources. | Why does it forget? | Logging done in try block, without finally clause. | Why is there no finally? | Developer was unaware of auto-closeable pattern. | Why no code review flagged it? | Logging changes merged directly to prod branch.
SPR105 | Alice | CT | CT scan image viewer not loading properly | The image viewer freezes when loading DICOM series in sequence. | Assigned | Stability Patch | 2.3.4 | - | Issue reproduced in test environment, logs collected. | Yes | Why does the viewer freeze? | Thread pool exhaustion due to high-res image processing. | Why is the pool exhausted? | Image loading is synchronous and blocks rendering thread. | Why is it synchronous? | Legacy code in Java Swing event dispatch thread. | Why is legacy code still used? | Refactoring plan delayed due to Q1 deadline. | Why was the deadline prioritized? | Customer demo required stable old features.
SPR106 | Bob | CT | Angular module crashes on patient report fetch | Clicking 'Fetch Reports' crashes the embedded Angular module intermittently. | In Progress | Q3 Roadmap | 1.1.2 | - | Issue reproduced in test environment, logs collected. | Yes | Why does the module crash? | Uncaught promise rejection on HTTP error. | Why is it uncaught? | Missing error handler in Angular service. | Why is handler missing? | Developer assumed HTTP interceptor would catch all errors. | Why is assumption wrong? | Interceptor only logs, doesn’t handle rejections. | Why wasn’t it caught in testing? | No test case for 404 response path.
SPR107 | Clara | CT | Delayed UI response during scan configuration | UI takes over 10 seconds to respond when configuring scan presets. | New | Q2 Fixes | 3.0.1 | - | Issue reproduced in test environment, logs collected. | Yes | Why is UI delayed? | Angular change detection takes too long. | Why is change detection slow? | Too many bound variables in scan config form. | Why so many variables? | All form fields are bound two-way unnecessarily. | Why was two-way binding used? | Copied from another module without optimization. | Why wasn't it reviewed? | Time constraints during integration sprint.
SPR108 | David | CT | NullPointerException in scan scheduler backend | Backend throws NullPointerException when scheduling overlapping scans. | Validated | Hotfix Batch | 1.0.0 | 4.1.0 | Issue reproduced in test environment, logs collected. | Yes | Why NPE in backend? | Null patient object passed to scheduler. | Why is patient null? | Scheduler triggered before patient assignment completes. | Why trigger before assignment? | Scan request UI sends async event prematurely. | Why is event premature? | UI does not await SpringBoot response completion. | Why doesn’t UI await response? | Missing promise chaining in embedded Angular.